## Sheet1
order_date | order_number | product_name | buyer | responsible | quantity | required_delivery | terms_of_delivery | payment_date | etd | eta | ata | transit_status | transport
2024-08-12 |  | Valsartan EP | AN | AK | 2000 |  | CC 5/2025 | 2025-05-12 | mid May |  |  | in process | sea
2024-08-12 |  | Valsartan EP | AN | AK | 3000 | end of Jan | Mixed 13/2024 | 2024-12-11 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-09-17 |  | Plasmapheresis Centrifuge Apparatus | AN | AK | 21000 | January 2025 | FOB Qingdao |  | 2024-11-20 | 2025-01-09 | 2025-01-25 | arrived | sea
2024-09-17 |  | Plasma collection sets | AN | AK | 24000 | January 2025 | FOB Shanghai | 2024-11-05 | 2024-11-14 | 2024-12-29 | 2025-01-05 | arrived | sea
2024-09-30 |  | Paracetamol | AN | SM | 7000 | January'25 | Mixed 12/2024 | 2024-11-19 | 2024-12-01 | 2025-01-10 | 2025-01-14 | arrived | sea
2024-10-04 | Z000615 | Paracetamol | AN | ED | 2000 |  | CC 1/2025 (FCA) | 2024-12-23 | 2025-01-20 | 2025-03-01 | 2025-03-24 | arrived | sea
2024-10-08 |  | Spironolactone | AN | SM | 500 | fresh batch | Mixed 13/2024 | 2024-12-04 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-10-09 | Z000696 | Pancreatin 45 | AN | ED | 8000 | end Dec or Jan | Mixed 12/2024 | 2024-11-19 | 2024-12-01 | 2025-01-10 | 2025-01-14 | arrived | sea
2024-10-25 |  | Plasma collection sets | AN | AK | 24000 | March 2025 | FOB Shanghai |  | 2025-01-06 | 2025-02-21 | 2025-03-09 | arrived | sea
2024-10-29 |  | RUTOCEL 60RT6 | AN | SS | 175 | January | Mixed 12/2024 | 2024-11-14 | 2024-12-01 | 2025-01-10 | 2025-01-14 | arrived | sea
2024-10-31 |  | Diphenhydramine HCL | AN | SS | 500 | early December | CIP air Hamburg | 2024-11-27 | 2025-01-06 | 2025-01-07 | 2025-01-09 | arrived | air
2024-11-04 | Z000645 | Magnesium carbonate heavy | AN | ED | 300 |  | Mixed 12/2024 | 2024-11-19 | 2024-12-01 | 2025-01-10 | 2025-01-14 | arrived | sea
2024-11-05 | Z000646 | Pyridoxine HCL / B6 | AN | SS/ED | 150+75 | January | Mixed 13/2024 | 2024-11-19 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-11-05 | Z000647 | Thiamine HCL / B1 | AN | SS/ED | 125+50 | January | Mixed 13/2024 | 2024-11-19 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-11-05 |  | Torasemide | AN | SS | 50 | January 2025 | Mixed 12/2024 (FCA) | 2024-11-19 | 2024-12-01 | 2025-01-10 | 2025-01-14 | arrived | sea
2024-11-06 |  | Doxicycline Monohydrate | AN | AK | 390 | ASAP | CIP air Tallinn | 2024-12-23 | 2025-01-06 | 2025-01-10 | 2024-10-13 | arrived | air
2024-11-06 |  | Doxicycline Monohydrate | AN | AK | 602.084 | ASAP | CIP air Tallinn | 2025-01-09 | 2025-01-22 | 2025-01-24 | 2025-01-25 | arrived | air
2024-11-06 | Z000649 | Pancreatin 67 | AN | ED | 600 | January | Mixed 12/2024 | 2024-11-19 | 2024-12-01 | 2025-01-10 | 2025-01-14 | arrived | sea
2024-11-12 |  | Bicillin-5 | AN | SS | 1120 | February | Mixed 13/2024 | 2024-12-04 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-11-12 | Z000656 | Linezolid | AN | ED | 40 |  | CIP air Hamburg | 2024-12-04 | 2025-01-06 | 2025-01-08 | 2025-01-08 | arrived | air
2024-11-25 |  | Gentamycin sulphate | AN | SS | 140 | bou/ Jan-Fenb | Mixed 13/2024 | 2024-12-04 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-11-25 |  | Anastrozole | AN | AK | 5.58 | till 02/01 in Dubai | CIP air Mumbai | 2024-12-23 | 2025-01-08 | 2025-01-09 | 2025-01-09 | arrived | air
2024-11-27 |  | Metamizole Sodium | AN | SM | 5000 |  | CC 1/2025 | 2025-01-08 | 2025-01-20 | 2025-03-01 | 2025-03-24 | arrived | sea
2024-11-28 | Z000692 | Magnesium carbonate heavy | AN | ED | 300 |  | Mixed 13/2024 | 2024-12-04 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-12-03 |  | Ketotifen | AN | SM | 5 |  | CIP air Hamburg | 2024-12-11 | 2025-01-04 | 2025-01-06 | 2025-01-06 | arrived | air
2024-12-06 |  | Fosfomycin Trometamol | AN | AK | 860 |  | CC 1/2025 | 2025-01-07 | 2025-01-20 | 2025-03-01 | 2025-03-24 | arrived | sea
2024-12-06 | Z000706 | Nitroxoline | AN | ED | 1000 |  | CIF sea Hamburg | 2024-12-17 | 2025-01-02 | 2025-02-13 | 2025-02-18 | arrived | air
2024-12-06 |  | Oxytetracycline HCL | JL | SM | 200 |  | CIP air Hamburg | 2024-12-12 | 2025-01-01 | 2025-01-03 | 2025-01-06 | arrived | air
2024-12-11 |  | Plasma collection sets | AN | AK | 24000 | March 2025 | FOB Shanghai | 2025-01-21 | 2025-02-12 | 2025-03-06 | 2025-03-30 | arrived | sea
2024-12-11 |  | Plasmapheresis Centrifuge Apparatus | AN | AK | 21000 | March 2025 | FOB Qingdao |  | 2025-01-24 | 2025-03-14 | 2025-03-26 | arrived | sea
2024-12-11 |  | Ciprofloxacin HCL | AN | SM | 3000 |  | Mixed 13/2024 | 2024-12-12 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-12-11 | Z000709 | Procaine HCL | AN | ED | 300 |  | Mixed 13/2024 | 2024-12-12 | 2024-12-24 | 2025-01-31 | 2025-01-31 | arrived | sea
2024-12-11 |  | Phenibut | AN | AK | 400 | Jan 25 | CIP air Hamburg | 2024-12-30 | 2025-01-08 | 2025-01-10 | 2025-01-10 | arrived | air
2024-12-11 | Z000708 | Nimesulide | AN | ED | 500 |  | CIP air Hamburg | 2024-12-17 | 2025-01-05 | 2025-01-06 | 2025-01-09 | arrived | air
2024-12-16 | Z000711 | Headcel 60HD6 | AN | ED | 1620 |  | CC 2/2025 | 2024-12-30 | 2025-03-11 | 2025-04-19 | 2025-04-21 | arrived | sea
2024-12-18 |  | Enalapril Maleate | AN | SS | 200 | March | CC 1/2025 | 2025-01-06 | 2025-01-20 | 2025-03-01 | 2025-03-24 | arrived | sea
2024-12-18 |  | Lincomycin HCL | AN | SS | 400 |  | FCA Shanghai/by air | 2025-02-28 | 2025-03-13 | 2025-03-17 | 2025-03-17 | arrived | sea
2024-12-27 |  | Anastrozole | AN | AK | 3.4 | February | CIP air Mumbai |  | 2025-02-24 | 2025-02-25 | 2025-02-25 | arrived | air
2024-12-30 |  | Unithiol sample | AN | SM | 0.1 |  | By courier | 2025-01-06 | 2025-01-16 | 2025-01-23 | 2025-01-23 | arrived | air
2025-01-02 | Z000724 | Chlorhexidine Gluconate | AN | ED | 1000 |  | CIF sea Hamburg | 2025-01-06 | 2025-01-21 | 2025-02-26 | 2025-03-01 | arrived | air
2025-01-06 |  | Plasmapheresis Centrifuge Apparatus | AN | AK | 21000 | April 2025 | FOB Qingdao |  | 2025-03-01 | 2025-04-17 | 2025-04-27 | arrived | sea
2025-01-06 |  | Plasma collection sets | AN | AK | 24000 | April 2025 | FOB Shanghai |  | 2025-02-26 | 2025-04-05 | 2025-04-07 | arrived | sea
2025-01-16 |  | Valsartan EP | AN | AK | 2000 |  | CC 2/2025 | 2025-02-18 | 2025-03-11 | 2025-04-19 | 2025-04-21 | arrived | sea
2025-01-23 |  | Magnesium carbonate heavy | AN | SM | 1200 |  | CC 2/2025 | 2025-02-11 | 2025-03-11 | 2025-04-19 | 2025-04-21 | arrived | sea
2025-01-23 |  | Pyrantel Pamoate | AN | AK | 3500 | 2025-03-25 | FCA Shanghai/LCL to Tallinn | 2025-01-27 | 2025-02-01 | 2025-03-26 | 2025-04-11 | arrived | sea
2025-01-23 |  | GABA sample | AN | AK | 0.1 |  | Free sample |  | 2025-01-23 | 2025-01-29 | 2025-01-29 | arrived | air
2025-01-27 |  | GABA sample | AN | AK | 0.1 |  | Free sample |  | 2025-01-27 | 2025-01-31 | 2025-01-31 | arrived | air
2025-02-06 | Z000729 | Smectite | JL | ED | 1100 | ASAP | CC 3/2025 | 2025-03-19 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-02-07 | Z000732 | Moxifloxacin HCL | JL | ED | 75 |  | CIP air Hamburg | 2025-02-11 | 2025-02-22 | 2025-02-25 | 2025-02-24 | arrived | air
2025-02-07 | Z000731 | Mefenamic acid | JL | ED | 150 |  | CIP air Hamburg | 2025-02-11 | 2025-02-16 | 2025-02-19 | 2025-02-19 | arrived | air
2025-02-12 |  | GABA sample | AN | AK | 0.1 |  | Free sample |  | 2025-02-12 | 2025-02-18 | 2025-02-18 | arrived | air
2025-02-12 |  | Anastrozole | AN | AK | 8 | till 7th of April | CIP air Mumbai | 2025-03-17 | 2025-04-03 | 2025-04-04 | 2025-04-05 | arrived | air
2025-02-12 |  | Plasmapheresis Centrifuge Apparatus | AN | AK | 21000 | June 2025 | FOB Qingdao |  | 2025-04-01 | 2025-05-20 | 2025-05-20 | en route | sea
2025-02-14 |  | Drotaverine HCL | AN | ED | 600 |  | CC 2/2025 | 2025-02-28 | 2025-03-11 | 2025-04-19 | 2025-04-21 | arrived | sea
2025-02-19 | Z000733 | Mefenamic acid | AN | ED | 200 |  | CC 2/2025 | 2025-02-24 | 2025-03-11 | 2025-04-19 | 2025-04-21 | arrived | sea
2025-02-19 |  | PVP K25 | JL | SM | 3000 | ASAP | CC 3/2025 | 2025-03-19 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-02-19 | Z000734 | Ascorbic acid | JL | ED | 500 | ASAP | CC 4/2025 (FCA) | 2025-04-02 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-02-20 |  | Betaine anhydrous | AN | ED | 25 |  | CIP air Hamburg | 2025-02-24 | 2025-03-09 | 2025-03-11 | 2025-03-11 | arrived | air
2025-02-24 |  | Nalbuphine HCL | AN | SM | 7 | ASAP | CIP air Hamburg |  | 2025-03-28 | 2025-03-29 | 2025-03-29 | arrived | air
2025-02-24 |  | Calcium Carbonate (Magnesia 444) | JL | SM | 10000 |  | CPT Reinbek | 2025-03-03 |  |  | 2025-04-17 | arrived | air
2025-02-25 | Z000735 | Drotaverine HCL | JL | SM | 600 | STOCK | CC 3/2025 | 2025-03-19 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-03-03 |  | L-Arginine USP preshipment samples | JL | AK | 0.18 |  | By courier |  | 2025-03-14 | 2025-03-19 | 2025-03-18 | arrived | air
2025-03-03 |  | Betaine anhydrous | JL | AK | 5500 | June in Kyiv | CC 3/2025 | 2025-03-03 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-03-03 | Z000747 | Betaine HCL | JL | AK | 5500 | June in Kyiv | CC 3/2025 | 2025-03-03 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-03-03 |  | L-Carnitine | JL | AK | 500 | June in Kyiv | CC 3/2025 | 2025-03-03 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-03-03 |  | L-Arginine USP | JL | AK | 5500 | June in Kyiv | CC 3/2025 | 2025-03-11 | 2025-04-16 | 2025-05-25 | 2025-05-29 | en route | sea
2025-03-03 |  | Betaines + L-Carnitine preshipment samples | JL | AK | 0.35 |  | Free sample |  | 2025-03-20 | 2025-03-26 | 2025-03-25 | arrived | air
2025-03-04 | Z000755 | Pancreatin 45 | JL | ED | 2000 | July in Kyiv | CC 4/2025 | 2025-03-19 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-03-05 | Z000756 | Benzocaine EP | JL | ED | 200 |  | CC 4/2025 | 2025-03-19 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-03-06 |  | Cardboard Ningbo Fold | AN | AK | 24.643 | ASAP | CIF sea Hamburg | 2025-04-02 | 2025-05-04 | 2025-06-18 | 2025-06-18 | en route | sea
2025-03-06 |  | Cardboard AllyKing Cream | AN | AK | 49.034 | ASAP | CIF sea Hamburg | 2025-04-02 | 2025-04-22 | 2025-06-02 | 2025-06-02 | en route | sea
2025-03-10 |  | Diphenhydramine HCL | AN | SS | 300 | 19.05 in Ham | CIP air Hamburg | 2025-05-14 | May |  |  | in process | air
2025-03-14 |  | Amoxicillin trihydrate | AN | SS | 2000 | end June | CC 4/2025 | 2025-04-02 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-03-14 |  | Fenpiverinium Bromide | AN | SM | 2.5 | 1,5 kg + 1 kg | CIP air Hamburg |  | 2025-05-30 | 2025-05-06 | 2025-05-07 | arrived | air
2025-03-14 |  | Pitofenone HCL | AN | SM | 75 | ASAP | CIP air Hamburg |  | 2025-05-30 | 2025-05-06 | 2025-05-07 | arrived | air
2025-03-14 |  | Amoxicillin trihydrate | AN | SS | 1000 | end of April | FOB Shanghai/by air | 2025-04-02 | 2025-04-24 | 2025-04-29 | 2025-04-30 | arrived | sea
2025-03-18 |  | Plasmapheresis Centrifuge Apparatus | AN | AK | 21000 | August 2025 | FOB Qingdao |  | May |  |  | in process | sea
2025-03-18 |  | Plasma collection sets | AN | AK | 24000 | August 2025 | FOB Shanghai |  | June |  |  | in process | sea
2025-03-19 |  | Fructose EP | AN | OL | 6000 | ASAP | CC 4/2025 | 2025-04-02 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-03-24 |  | Anastrozole | AN | AK | 1.328 | till 7th April | CIP air Mumbai |  | 2025-04-03 | 2025-04-04 | 2025-04-05 | arrived | air
2025-03-25 | Z000761 | Mefenamic acid | AN | ED | 350 |  | CC 4/2025 | 2025-03-27 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-03-25 | Z000760 | Mefenamic acid | AN | ED | 150 | ASAP | CIP air Hamburg | 2025-03-27 | 2025-04-03 | 2025-04-07 | 2025-04-07 | arrived | air
2025-03-27 |  | Amoxicillin trihydrate | AN | SS | 3000 | end July (beg Aug) | CC 5/2025 | 2025-05-12 | ready |  |  | in process | sea
2025-03-27 |  | Amoxicillin trihydrate | AN | SS | 3000 | September | FOB Shanghai |  | June-July |  |  | in process | sea
2025-04-09 | Z000774 | Ibuprofen inj grade | AN | ED | 25 |  | CC 4/2025 (FCA) | 2025-04-17 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-04-14 | Z000773 | Pancreatin 67 | AN | ED | 1600 | ASAP | CC 5/2025 | 2025-05-12 | mid May |  |  | in process | sea
2025-04-14 | Z000775 | Pancreatin 67 | AN | ED | 800 | IV квартал | FOB Shanghai |  | September |  |  | in process | sea
2025-04-15 | Z000777 | Dextran 70 inj grade | AN | ED | 25 |  | CC 4/2025 | 2025-04-17 | 2025-05-01 | 2025-06-12 | 2025-06-15 | en route | sea
2025-04-16 |  | Rivaroxaban | AN | SM | 2.5 | ASAP | CIP air Hamburg | 2025-04-17 | 2025-04-26 | 2025-04-28 | 2025-04-28 | arrived | air
2025-04-24 | Z000778 | L-Tryptophan | AN | ED | 100 | end July in Ham | CC 5/2025 | 2025-05-12 |  |  |  | in process | sea
2025-04-25 |  | GABA | AN | AK | 200 |  | CC 5/2025 | 2025-05-12 |  |  |  | in process | sea
2025-04-25 |  | Plasma collection sets | AN | AK | 24000 | September 2025 | FOB Shanghai |  | July |  |  | in process | sea
2025-05-06 | Z000781 | Linezolid | AN | ED | 100 |  | CIP air Hamburg |  |  |  |  | in process | air
2025-05-08 |  | Unithiol | JL | SM | 2 | June | CIP air Hamburg |  | June |  |  | in process | air